## 🏗️ Builder
CASH FLOW OFFICE ¦ Job Cost Tracker — Builder (Draw-Based Projects)
Project Name: |  | Client: |  | Project Manager: |  | Start Date: |  | Report Date:
Retainage Rate: | 10% | ← Enter your contract retainage rate (typically 5% or 10%). This drives the Retainage Held column automatically.
JOB INFO |  |  |  | BUDGET |  |  | SUBCONTRACT |  |  | COST TRACKING |  |  |  | PERFORMANCE |  | BILLING |  |  | COLLECTIONS & RETAINAGE |  |  | STATUS
Cost Code | Draw # / Milestone | Trade / Description | Contractor / Sub | Original Budget | Approved Change Orders | Revised Budget ▶ | Orig Sub Contract | Sub Change Orders | Revised Sub Contract ▶ | Committed Cost to Date | Non-Committed Cost to Date | Non-Committed Est. to Complete | Est. Final Cost ▶ | Variance ▶ (Budget−Final) | % Complete (Est.) | Amount Billed | Retainage Held ▶ | Net Billed (After Ret.) ▶ | Amount Collected | Retainage Released | Retainage Outstanding ▶ | Job Status
101 | Draw 1 | Supervision |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
102 | Draw 1 | Project Management |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
120 | Draw 1 | Temporary Facilities |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
220 | Draw 2 | Earthwork |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
340 | Draw 2 | Concrete Labor |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
340 | Draw 2 | Concrete Materials |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
340 | Draw 2 | Concrete Equipment |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
510 | Draw 3 | Steel / Structural |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
750 | Draw 3 | Roofing |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
910 | Draw 4 | Plaster / Drywall |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
1540 | Draw 4 | Plumbing |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
1600 | Draw 4 | Electrical |  |  |  | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
[6 empty] | 0 |  |  | 0 |  |  |  | 0 | 0 |  |  | 0 | 0 |  |  | 0
SUB-TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Insurance / Bonding
OH + Profit
TOTALS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CASH POSITION SUMMARY
Contract Value (Revised Budget) |  |  |  |  | 0
Total Billed |  |  |  |  | 0
Retainage Held (withheld by Owner) |  |  |  |  | 0
Net Billed (After Retainage) |  |  |  |  | 0
Total Collected |  |  |  |  | 0
Retainage Released |  |  |  |  | 0
Retainage Still Outstanding |  |  |  |  | 0
Est. Final Cost |  |  |  |  | 0
Projected Profit ($) |  |  |  |  | 0
Projected Profit (%) |  |  |  |  | 0%
Cash Gap (Billed − Collected) |  |  |  |  | 0
Cash Position (Collected − Costs) |  |  |  |  | 0
⚠ Retainage is cash you've earned but cannot collect until job completion/acceptance. Track it carefully — it's often 5-10% of your entire contract value tied up for months.
CASH RISK SCORE
Score ( 1 = High Risk → 10 = Low Risk ) |  |  |  |  | 5
🔴 1–3 High Risk ¦ 🟡 4–6 Monitor ¦ 🟢 7–10 Healthy · Factors: Profit, Variance, Cash Position, Outstanding Balance
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 🔧 Subcontractor
CASH FLOW OFFICE ¦ Job Cost Tracker — Subcontractor (Cash Lag Model)
Project Name: |  | Client: |  | Project Manager: |  | Start Date: |  | Report Date:
Retainage Rate: | 10% | ← Retainage rate withheld by your GC (typically 5–10%). Drives Retainage Held column.
JOB INFO |  |  | INVOICE |  |  | CASH RECEIVED & TIMING |  |  | RETAINAGE |  |  | COSTS |  | GROSS PROFIT ▶ | CASH POSITION ▶ | LIEN WAIVER | STATUS
Job Code | Job Name / GC Project | General Contractor | Invoice Amount | Invoice Date | Invoice # / Ref | Expected Pay Date | Cash Received | Days to Collect ▶ | Retainage Held ▶ | Retainage Released | Retainage Outstanding ▶ | Labor Cost | Materials Cost | Gross Profit ▶ | Cash Position ▶ | Lien Waiver Signed? | Job Status
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
[9 empty] | 0 |  | 0
TOTALS |  |  | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
CASH LAG SUMMARY
Total Invoiced |  |  |  |  | 0
Total Collected |  |  |  |  | 0
Outstanding (Not Collected) |  |  |  |  | 0
Retainage Held by GC |  |  |  |  | 0
Retainage Released |  |  |  |  | 0
Retainage Still Outstanding |  |  |  |  | 0
Total Labor Cost |  |  |  |  | 0
Total Materials Cost |  |  |  |  | 0
Total Cost |  |  |  |  | 0
Gross Profit ($) |  |  |  |  | 0
Gross Profit (%) |  |  |  |  | 0%
Cash Position |  |  |  |  | 0
⚠ Lien Waiver must be signed upon final payment. Unsigned lien waivers = your right to file a mechanics lien is still open. Track this on every job — it's your last line of defense if a GC doesn't pay.
CASH RISK SCORE
Score ( 1 = High Risk → 10 = Low Risk ) |  |  |  |  | 5
🔴 1–3 High Risk ¦ 🟡 4–6 Monitor ¦ 🟢 7–10 Healthy · Factors: Profit, Variance, Cash Position, Outstanding Balance
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 🏡 Remodeler
CASH FLOW OFFICE ¦ Job Cost Tracker — Remodeler (Change Order Driven)
Project Name: |  | Client: |  | Project Manager: |  | Start Date: |  | Report Date:
Retainage Rate: | 10% | ← Retainage rate (if applicable — not all remodel contracts use retainage). Set to 0% if none.
JOB INFO |  | SUB / VENDOR | CONTRACT & CHANGE ORDERS |  |  | REVISED CONTRACT ▶ | BILLING & COLLECTIONS |  | RETAINAGE |  |  | COSTS |  |  |  | GROSS PROFIT ▶ | CASH POSITION ▶ | STATUS
Cost Code | Scope / Description | Sub / Vendor | Original Contract | Change Order Amount (+/−) | CO Status | Revised Contract ▶ | Invoiced / Billed | Collected | Retainage Held ▶ | Retainage Released | Retainage Outstanding ▶ | Labor Cost | Materials Cost | Sub Cost | Cash Paid | Gross Profit ▶ | Cash Position ▶ | Job Status
101 | Demo & Site Prep |  |  |  |  | 0 |  |  | 0 |  | 0
201 | Framing |  |  |  |  | 0 |  |  | 0 |  | 0
301 | Rough Plumbing |  |  |  |  | 0 |  |  | 0 |  | 0
302 | Rough Electrical |  |  |  |  | 0 |  |  | 0 |  | 0
401 | Insulation |  |  |  |  | 0 |  |  | 0 |  | 0
501 | Drywall |  |  |  |  | 0 |  |  | 0 |  | 0
601 | Tile / Flooring |  |  |  |  | 0 |  |  | 0 |  | 0
701 | Cabinets & Millwork |  |  |  |  | 0 |  |  | 0 |  | 0
801 | Painting |  |  |  |  | 0 |  |  | 0 |  | 0
901 | Finish Plumbing |  |  |  |  | 0 |  |  | 0 |  | 0
902 | Finish Electrical |  |  |  |  | 0 |  |  | 0 |  | 0
1001 | Final Clean / Punch |  |  |  |  | 0 |  |  | 0 |  | 0
[6 empty] | 0 |  |  | 0 |  | 0
[6 empty] | 0 |  |  | 0 |  | 0
[6 empty] | 0 |  |  | 0 |  | 0
[6 empty] | 0 |  |  | 0 |  | 0
[6 empty] | 0 |  |  | 0 |  | 0
[6 empty] | 0 |  |  | 0 |  | 0
[6 empty] | 0 |  |  | 0 |  | 0
[6 empty] | 0 |  |  | 0 |  | 0
TOTALS |  |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CHANGE ORDER & PROFIT SUMMARY
Original Contract Total |  |  |  |  | 0
Total Change Orders |  |  |  |  | 0
Revised Contract Total |  |  |  |  | 0
Total Billed / Invoiced |  |  |  |  | 0
Total Collected |  |  |  |  | 0
Uncollected Balance |  |  |  |  | 0
Retainage Held |  |  |  |  | 0
Retainage Released |  |  |  |  | 0
Retainage Outstanding |  |  |  |  | 0
Total Costs (L+M+S) |  |  |  |  | 0
Gross Profit ($) |  |  |  |  | 0
Gross Profit (%) |  |  |  |  | 0%
Cash Position |  |  |  |  | 0
⚠ CO RISK: Never perform work on an unapproved Change Order. Set CO Status to 'Approved' before proceeding. Unapproved COs = work you may never get paid for. ¦ ⚠ RETAINAGE RISK: Collect final payment + retainage release before signing off on completion.
CASH RISK SCORE
Score ( 1 = High Risk → 10 = Low Risk ) |  |  |  |  | 5
🔴 1–3 High Risk ¦ 🟡 4–6 Monitor ¦ 🟢 7–10 Healthy · Factors: Profit, Variance, Cash Position, Outstanding Balance
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 📖 Cost Code Reference
CASH FLOW OFFICE ¦ Cost Code Reference — Common Construction Categories
These are commonly used construction cost code categories based on CSI MasterFormat conventions. They are NOT universal — every company may use different codes. Use these as a starting point and adjust to match your system.
| Cost Code | Category Name | Typical Line Items | Used By
── GENERAL CONDITIONS (000–199)
| 101 | Supervision | Project superintendent, PM time on site | Builder
| 102 | Project Management | Office PM time, scheduling, coordination | Builder
| 103 | Safety | Safety equipment, training, signage | Builder
| 110 | Temporary Facilities | Temp power, water, toilets, fencing | Builder, Remodeler
| 120 | Cleanup / Debris Removal | Dumpsters, haul-off, final clean | All
── SITEWORK (200–299)
| 210 | Site Preparation | Demolition, clearing, grubbing | Builder, Remodeler
| 220 | Earthwork | Grading, excavation, backfill, compaction | Builder
| 230 | Utilities — Underground | Water, sewer, gas, conduit below grade | Builder, Sub
| 240 | Paving / Flatwork | Driveways, sidewalks, parking, curbs | Builder, Sub
── CONCRETE (300–399)
| 310 | Foundations | Footings, piers, stem walls, grade beams | Builder, Sub
| 320 | Slab on Grade | Floor slabs, SOG, flatwork | Builder, Sub
| 330 | Concrete Labor | Forming, pouring, finishing labor | Builder, Sub
| 340 | Concrete Materials | Ready-mix, rebar, wire mesh | Builder
| 350 | Concrete Equipment | Pump trucks, vibrators, forms rental | Builder
── STRUCTURAL (400–599)
| 410 | Masonry | CMU block, brick, stone, mortar | Builder, Sub
| 510 | Structural Steel | Beams, columns, joists, decking | Builder, Sub
| 520 | Framing — Wood | Lumber, LVL, trusses, sheathing | Builder, Remodeler, Sub
| 530 | Framing Labor | Framing crew, layout, blocking | Builder, Remodeler, Sub
── EXTERIOR (600–699)
| 610 | Roofing | Shingles, tile, metal, underlayment, flashing | Builder, Remodeler, Sub
| 620 | Exterior Cladding | Siding, stucco, EIFS, trim, soffit, fascia | Builder, Remodeler, Sub
| 630 | Windows & Doors | Supply and install windows, exterior doors | Builder, Remodeler
| 640 | Waterproofing | Membrane, sealants, drainage board | Builder, Sub
── MEP (700–999)
| 710 | HVAC | Equipment, ductwork, venting, controls | Builder, Sub
| 720 | Plumbing — Rough | Supply, DWV, underground, stub-outs | Builder, Sub
| 730 | Plumbing — Finish | Fixtures, trim, appliances, connections | Builder, Remodeler, Sub
| 810 | Electrical — Rough | Panel, conduit, wire, boxes, rough-in | Builder, Sub
| 820 | Electrical — Finish | Devices, fixtures, trim, final connections | Builder, Remodeler, Sub
| 910 | Low Voltage / Data | Security, camera, AV, data, intercoms | Builder, Sub
── INTERIOR FINISHES (1000–1499)
| 1010 | Insulation | Batt, spray foam, rigid, blown-in | Builder, Remodeler, Sub
| 1020 | Drywall | Hanging, taping, finish, texture | Builder, Remodeler, Sub
| 1030 | Painting — Interior | Prime, paint, ceilings, walls, trim | Builder, Remodeler, Sub
| 1040 | Tile & Stone | Floor tile, wall tile, backsplash, stone | Builder, Remodeler, Sub
| 1050 | Flooring | Hardwood, LVP, carpet, installation | Builder, Remodeler
| 1060 | Cabinets & Millwork | Kitchen/bath cabinets, built-ins, trim carpentry | Builder, Remodeler
| 1070 | Countertops | Granite, quartz, laminate, fabricate & install | Builder, Remodeler
| 1080 | Interior Doors & Hardware | Pre-hung doors, slabs, hardware, closets | Builder, Remodeler
── SPECIALTY & OTHER (1500–1999)
| 1510 | Appliances | Supply and install kitchen, laundry appliances | Builder, Remodeler
| 1520 | Landscaping | Sod, plants, irrigation, grading, tree work | Builder
| 1530 | Pool / Hardscape | Pool, patio, deck, outdoor kitchen, pavers | Builder, Remodeler
| 1540 | Elevator / Specialty | Elevator, dumbwaiter, specialty systems | Builder
── OVERHEAD & PROFIT (2000+)
| 2000 | General Overhead | Office rent, utilities, admin staff, vehicles | Builder, Remodeler
| 2001 | Insurance / Bonding | GL, builder's risk, WC, bond premiums | All
| 2002 | Warranty Reserve | Callback allowance, warranty work reserve | Builder, Remodeler
| 2003 | Profit / Fee | Builder's profit margin, management fee | All
── SUBCONTRACTOR JOB TYPES (Sub Tab Reference)
| SUB-01 | Electrical Sub | Panel, rough, finish, service, low volt | Sub
| SUB-02 | Plumbing Sub | Water, DWV, gas, fixtures, rough + finish | Sub
| SUB-03 | HVAC Sub | Equipment, duct, venting, controls, startup | Sub
| SUB-04 | Framing Sub | Structural framing, sheathing, blocking | Sub
| SUB-05 | Roofing Sub | Tear-off, install, flashing, warranty | Sub
| SUB-06 | Drywall Sub | Hang, tape, texture, finish | Sub
| SUB-07 | Painting Sub | Interior/exterior painting, prime, caulk | Sub
| SUB-08 | Tile Sub | Floor, wall, backsplash, shower, stone | Sub
| SUB-09 | Concrete Sub | Foundations, flatwork, slabs, decorative | Sub
| SUB-10 | Masonry Sub | Block, brick, stone, mortar, waterproofing | Sub
NOTE: Codes follow CSI MasterFormat conventions — widely used in Sage 300, Procore, Viewpoint, Buildertrend. Your GC or accounting system may use different numbering. Cost code columns in all tracker tabs are unlocked for editing.
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 📋 Instructions
CASH FLOW OFFICE ¦ Job Cost Tracker v3 — How to Use This Workbook
This workbook has 5 tabs: Builder, Subcontractor, Remodeler, Cost Code Reference, and Instructions. Choose the tracker that matches your business type. These are DECISION tools — not accounting reports. They answer 3 questions instantly: 1. Am I making money on this job? 2. Have I collected enough to cover what I've paid? 3. Is retainage building up and when will I get it back?
WHICH TAB TO USE
| 🏗️ Builder Tab | Draw-based / staged payment projects. Best for custom home builders and spec builders. Includes Draw # / Milestone column, % Complete, and full retainage tracking.
| 🔧 Subcontractor Tab | Cash lag model. Tracks invoices vs. collections, Days to Collect, GC retainage withheld, and Lien Waiver status. Best for trade contractors (electricians, plumbers, HVAC, etc.).
| 🏡 Remodeler Tab | Change order driven. Tracks CO Status (Requested → Approved → Billed → Collected), retainage, and whether collected cash covers what you've paid. Best for kitchen/bath and renovation contractors.
RETAINAGE — WHAT IS IT AND WHY IT MATTERS
| What is Retainage? | Retainage (also called 'retention') is a percentage — typically 5% or 10% — that the owner or GC withholds from every payment until the job is substantially complete. It's your money, but you can't touch it until final acceptance. On a $500K job at 10% retainage, that's $50,000 tied up — sometimes for 6–12 months.
| How to use the Retainage Rate cell | Enter your contract retainage rate in the yellow cell (B3) at the top of each tab. The Retainage Held column calculates automatically on every billing row. Track Retainage Released manually as the owner releases it at job milestones or final completion.
CHANGE ORDERS — STATUS MATTERS
| CO Status dropdown (Remodeler) | Requested = you've asked for it, not yet approved. Approved = GC/owner signed off — you can proceed. Billed = you've invoiced for it. Collected = cash received. ⚠ Never start work on a Requested CO — only proceed once it shows Approved.
| Why this matters | Change orders are the #1 source of remodeler disputes and unpaid work. If a CO is Requested but not Approved and the project stops, you may have no legal right to collect. The CO Status column keeps this visible at all times.
LIEN WAIVERS (Subcontractor Tab)
| What is a Lien Waiver? | A lien waiver is a document you sign when you receive payment, waiving your right to file a mechanics lien for that payment amount. GCs typically require it before releasing payment. Do NOT sign a lien waiver before receiving the check — or before it clears.
| Lien Waiver Signed? column | Yes = signed and delivered. No = not yet signed — lien rights still open. Partial = conditional waiver signed (you signed for partial payment, lien rights remain for the balance). This column protects you — it shows exactly where your lien rights stand on every job.
COLUMN COLOR GUIDE
| 🟡 Yellow | Input cells — enter your data here. Never locked.
| 🔵 Blue (▶ columns) | Formula cells — auto-calculated. Locked. Do not overwrite.
| 🟣 Purple | Retainage columns — special attention required. Tracks cash you've earned but can't access yet.
| 🟦 Teal | Lien Waiver column (Sub tab). Legal protection tracking.
| 🔴 Red highlight | Negative cash position, over-budget variance, or unpaid/unsigned items. Needs attention.
| 🟢 Green highlight | Positive cash position or favorable variance. Healthy.
PROTECTION NOTES
| Formula cells are locked | Blue cells and headers are protected from accidental edits. To unprotect: Review → Unprotect Sheet → Password: CFO2026
| Input cells are always editable | No password needed for normal data entry.
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026