## 📊 Master Summary
CASH FLOW OFFICE ¦ 13-Week Master Cash Flow Summary — All Jobs
Company: |  |  | Owner / PM: |  |  | Period Start: |  |  | Report Date:
🔴 Company Red Zone Threshold: | 10000 | ← Minimum combined cash across all jobs. Set this at the company level — typically higher than any single job threshold.
JOB / METRIC |  | 13-WK TOTAL | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Week Starting Date → |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
▼ WEEKLY CASH FLOW BY JOB
Job 1
Total Inflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Cash Flow |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ending Cash Balance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Job 2
Total Inflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Cash Flow |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ending Cash Balance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Job 3
Total Inflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Cash Flow |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ending Cash Balance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Job 4
Total Inflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Cash Flow |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ending Cash Balance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Job 5
Total Inflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflows |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Cash Flow |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ending Cash Balance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
▼ COMPANY-WIDE TOTALS
Total Inflows — All Jobs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Outflows — All Jobs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Cash Flow — All Jobs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Combined Ending Cash Balance |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMBINED ENDING CASH COLOR GUIDE: 🔴 Red = Below Company Red Zone 🟠 Orange = Within 20% above threshold 🟢 Green = Healthy
COMPANY CASH HEALTH SNAPSHOT
Total 13-Week Inflows (All Jobs) |  |  | 0: 0
Total 13-Week Outflows (All Jobs) |  |  | 0: 0
Net Cash Flow — 13 Weeks |  |  | 0: 0
Closing Combined Cash (Week 13) |  |  | 0: 0
Lowest Combined Cash (Any Week) |  |  | 0: 0
Total Weeks Any Job Below Red Zone |  |  | 0: 65
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 📋 Job 1
CASH FLOW OFFICE ¦ 13-Week Cash Flow Planner — Job 1
Job / Project: |  |  | Client: |  |  | Project Manager: |  |  | Report Date:
Opening Cash Balance: | 0 |  |  | 🔴 Red Zone Threshold: | 5000 | ← Enter the minimum cash balance you want to maintain at all times. Weeks falling below this trigger a red alert.
CATEGORY |  | NOTES / ANNUAL | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13
Week Starting Date →
▼ CASH INFLOWS
Draw Requests / Progress Billings |  | Expected draw receipts from owner/GC this week
Retainage Releases |  | Retainage dollars expected to be released/paid this week
Customer Deposits |  | Upfront deposits or milestone deposits from clients
Other Income |  | Any other cash inflows (insurance proceeds, reimbursements, etc.)
TOTAL INFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
▼ CASH OUTFLOWS
Payroll / Labor |  | Gross payroll including owner salary if paid through payroll
Subcontractor Payments |  | Payments to subs — note: pay-when-paid clauses may shift timing
Material Purchases |  | Lumber, concrete, MEP materials, finishes, etc.
Equipment Rental |  | Crane, excavator, lift, scaffolding, tool rentals
Overhead (Rent, Insurance, Utilities, Admin) |  | Fixed overhead — same each week. Enter monthly ÷ 4.33 for weekly
Loan / Line of Credit Payments |  | Scheduled debt service or LOC draws/repayments
Owner Draw / Distributions |  | Cash taken out by owner(s) — critical to track for cash planning
Other Outflows |  | Permits, fees, unexpected costs, tax payments, etc.
TOTAL OUTFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NET CASH FLOW |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH BALANCE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH COLOR GUIDE: 🔴 Red = Below Red Zone threshold (danger) 🟠 Orange = Within 20% above threshold (warning) 🟢 Green = Healthy (≥ 120% of threshold)
13-WEEK SUMMARY
Opening Cash Balance |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Inflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Outflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Net Cash Flow (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Closing Cash (End of Week 13) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Lowest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Highest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Weeks Below Red Zone Threshold |  |  | 🔴 Red Zone Threshold: WEEK 2: 13
Total Draw Requests Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Retainage Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Payroll (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Sub Payments (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 📋 Job 2
CASH FLOW OFFICE ¦ 13-Week Cash Flow Planner — Job 2
Job / Project: |  |  | Client: |  |  | Project Manager: |  |  | Report Date:
Opening Cash Balance: | 0 |  |  | 🔴 Red Zone Threshold: | 5000 | ← Enter the minimum cash balance you want to maintain at all times. Weeks falling below this trigger a red alert.
CATEGORY |  | NOTES / ANNUAL | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13
Week Starting Date →
▼ CASH INFLOWS
Draw Requests / Progress Billings |  | Expected draw receipts from owner/GC this week
Retainage Releases |  | Retainage dollars expected to be released/paid this week
Customer Deposits |  | Upfront deposits or milestone deposits from clients
Other Income |  | Any other cash inflows (insurance proceeds, reimbursements, etc.)
TOTAL INFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
▼ CASH OUTFLOWS
Payroll / Labor |  | Gross payroll including owner salary if paid through payroll
Subcontractor Payments |  | Payments to subs — note: pay-when-paid clauses may shift timing
Material Purchases |  | Lumber, concrete, MEP materials, finishes, etc.
Equipment Rental |  | Crane, excavator, lift, scaffolding, tool rentals
Overhead (Rent, Insurance, Utilities, Admin) |  | Fixed overhead — same each week. Enter monthly ÷ 4.33 for weekly
Loan / Line of Credit Payments |  | Scheduled debt service or LOC draws/repayments
Owner Draw / Distributions |  | Cash taken out by owner(s) — critical to track for cash planning
Other Outflows |  | Permits, fees, unexpected costs, tax payments, etc.
TOTAL OUTFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NET CASH FLOW |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH BALANCE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH COLOR GUIDE: 🔴 Red = Below Red Zone threshold (danger) 🟠 Orange = Within 20% above threshold (warning) 🟢 Green = Healthy (≥ 120% of threshold)
13-WEEK SUMMARY
Opening Cash Balance |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Inflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Outflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Net Cash Flow (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Closing Cash (End of Week 13) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Lowest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Highest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Weeks Below Red Zone Threshold |  |  | 🔴 Red Zone Threshold: WEEK 2: 13
Total Draw Requests Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Retainage Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Payroll (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Sub Payments (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 📋 Job 3
CASH FLOW OFFICE ¦ 13-Week Cash Flow Planner — Job 3
Job / Project: |  |  | Client: |  |  | Project Manager: |  |  | Report Date:
Opening Cash Balance: | 0 |  |  | 🔴 Red Zone Threshold: | 5000 | ← Enter the minimum cash balance you want to maintain at all times. Weeks falling below this trigger a red alert.
CATEGORY |  | NOTES / ANNUAL | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13
Week Starting Date →
▼ CASH INFLOWS
Draw Requests / Progress Billings |  | Expected draw receipts from owner/GC this week
Retainage Releases |  | Retainage dollars expected to be released/paid this week
Customer Deposits |  | Upfront deposits or milestone deposits from clients
Other Income |  | Any other cash inflows (insurance proceeds, reimbursements, etc.)
TOTAL INFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
▼ CASH OUTFLOWS
Payroll / Labor |  | Gross payroll including owner salary if paid through payroll
Subcontractor Payments |  | Payments to subs — note: pay-when-paid clauses may shift timing
Material Purchases |  | Lumber, concrete, MEP materials, finishes, etc.
Equipment Rental |  | Crane, excavator, lift, scaffolding, tool rentals
Overhead (Rent, Insurance, Utilities, Admin) |  | Fixed overhead — same each week. Enter monthly ÷ 4.33 for weekly
Loan / Line of Credit Payments |  | Scheduled debt service or LOC draws/repayments
Owner Draw / Distributions |  | Cash taken out by owner(s) — critical to track for cash planning
Other Outflows |  | Permits, fees, unexpected costs, tax payments, etc.
TOTAL OUTFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NET CASH FLOW |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH BALANCE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH COLOR GUIDE: 🔴 Red = Below Red Zone threshold (danger) 🟠 Orange = Within 20% above threshold (warning) 🟢 Green = Healthy (≥ 120% of threshold)
13-WEEK SUMMARY
Opening Cash Balance |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Inflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Outflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Net Cash Flow (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Closing Cash (End of Week 13) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Lowest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Highest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Weeks Below Red Zone Threshold |  |  | 🔴 Red Zone Threshold: WEEK 2: 13
Total Draw Requests Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Retainage Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Payroll (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Sub Payments (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 📋 Job 4
CASH FLOW OFFICE ¦ 13-Week Cash Flow Planner — Job 4
Job / Project: |  |  | Client: |  |  | Project Manager: |  |  | Report Date:
Opening Cash Balance: | 0 |  |  | 🔴 Red Zone Threshold: | 5000 | ← Enter the minimum cash balance you want to maintain at all times. Weeks falling below this trigger a red alert.
CATEGORY |  | NOTES / ANNUAL | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13
Week Starting Date →
▼ CASH INFLOWS
Draw Requests / Progress Billings |  | Expected draw receipts from owner/GC this week
Retainage Releases |  | Retainage dollars expected to be released/paid this week
Customer Deposits |  | Upfront deposits or milestone deposits from clients
Other Income |  | Any other cash inflows (insurance proceeds, reimbursements, etc.)
TOTAL INFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
▼ CASH OUTFLOWS
Payroll / Labor |  | Gross payroll including owner salary if paid through payroll
Subcontractor Payments |  | Payments to subs — note: pay-when-paid clauses may shift timing
Material Purchases |  | Lumber, concrete, MEP materials, finishes, etc.
Equipment Rental |  | Crane, excavator, lift, scaffolding, tool rentals
Overhead (Rent, Insurance, Utilities, Admin) |  | Fixed overhead — same each week. Enter monthly ÷ 4.33 for weekly
Loan / Line of Credit Payments |  | Scheduled debt service or LOC draws/repayments
Owner Draw / Distributions |  | Cash taken out by owner(s) — critical to track for cash planning
Other Outflows |  | Permits, fees, unexpected costs, tax payments, etc.
TOTAL OUTFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NET CASH FLOW |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH BALANCE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH COLOR GUIDE: 🔴 Red = Below Red Zone threshold (danger) 🟠 Orange = Within 20% above threshold (warning) 🟢 Green = Healthy (≥ 120% of threshold)
13-WEEK SUMMARY
Opening Cash Balance |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Inflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Outflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Net Cash Flow (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Closing Cash (End of Week 13) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Lowest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Highest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Weeks Below Red Zone Threshold |  |  | 🔴 Red Zone Threshold: WEEK 2: 13
Total Draw Requests Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Retainage Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Payroll (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Sub Payments (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 📋 Job 5
CASH FLOW OFFICE ¦ 13-Week Cash Flow Planner — Job 5
Job / Project: |  |  | Client: |  |  | Project Manager: |  |  | Report Date:
Opening Cash Balance: | 0 |  |  | 🔴 Red Zone Threshold: | 5000 | ← Enter the minimum cash balance you want to maintain at all times. Weeks falling below this trigger a red alert.
CATEGORY |  | NOTES / ANNUAL | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13
Week Starting Date →
▼ CASH INFLOWS
Draw Requests / Progress Billings |  | Expected draw receipts from owner/GC this week
Retainage Releases |  | Retainage dollars expected to be released/paid this week
Customer Deposits |  | Upfront deposits or milestone deposits from clients
Other Income |  | Any other cash inflows (insurance proceeds, reimbursements, etc.)
TOTAL INFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
▼ CASH OUTFLOWS
Payroll / Labor |  | Gross payroll including owner salary if paid through payroll
Subcontractor Payments |  | Payments to subs — note: pay-when-paid clauses may shift timing
Material Purchases |  | Lumber, concrete, MEP materials, finishes, etc.
Equipment Rental |  | Crane, excavator, lift, scaffolding, tool rentals
Overhead (Rent, Insurance, Utilities, Admin) |  | Fixed overhead — same each week. Enter monthly ÷ 4.33 for weekly
Loan / Line of Credit Payments |  | Scheduled debt service or LOC draws/repayments
Owner Draw / Distributions |  | Cash taken out by owner(s) — critical to track for cash planning
Other Outflows |  | Permits, fees, unexpected costs, tax payments, etc.
TOTAL OUTFLOWS |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NET CASH FLOW |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH BALANCE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ENDING CASH COLOR GUIDE: 🔴 Red = Below Red Zone threshold (danger) 🟠 Orange = Within 20% above threshold (warning) 🟢 Green = Healthy (≥ 120% of threshold)
13-WEEK SUMMARY
Opening Cash Balance |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Inflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total 13-Week Outflows |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Net Cash Flow (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Closing Cash (End of Week 13) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Lowest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Highest Ending Cash (Any Week) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Weeks Below Red Zone Threshold |  |  | 🔴 Red Zone Threshold: WEEK 2: 13
Total Draw Requests Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Retainage Expected |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Payroll (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Total Sub Payments (13 Weeks) |  |  | 🔴 Red Zone Threshold: WEEK 2: 0
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026

## 📋 Instructions
CASH FLOW OFFICE ¦ 13-Week Cash Flow Planner — How to Use This Workbook
This workbook has 7 tabs: Master Summary + 5 individual Job Cash Flow Planners + Instructions. Purpose: See exactly what cash is coming in and going out — week by week — for 13 weeks (90 days). This is a FORWARD-LOOKING decision tool. It answers: • Will I have enough cash to make payroll next week? • When will my next draw hit, and what do I need to pay before it does? • Which weeks are dangerous — and what can I do now to prevent a cash crisis?
STEP 1 — SET UP EACH JOB TAB FIRST
| Name your Job tabs | The 5 job tabs are pre-labeled Job 1–5. You can rename them in Excel by right-clicking the tab. Enter the job/project name, client, PM, and report date in the yellow header cells at the top.
| Enter Opening Cash Balance | Row 3, left side. Enter the current cash balance for this job at the start of Week 1. This seeds the rolling ending cash calculation for all 13 weeks.
| Set your Red Zone Threshold | Row 3, right side. Enter the minimum cash balance you want to maintain. This is your safety net — below this number, you're in danger. Typical contractors set this at 1–2 weeks of payroll. The ending cash row turns red automatically when you hit it.
STEP 2 — ENTER WEEK START DATES
| Row 6 — date inputs | Enter the Monday (or first day) of each week in row 6. These are input cells — enter Week 1's date and the Master Summary tab will pull dates from Job 1 automatically.
STEP 3 — FILL IN INFLOWS AND OUTFLOWS WEEKLY
| INFLOWS (green section) | Draw Requests / Progress Billings: Enter the EXPECTED RECEIPT date — not when you submitted the draw. Draws typically take 2–3 weeks from submission to cash in your account. Build in that lag. Retainage Releases: Only enter when you expect actual payment — not when it's theoretically owed. Customer Deposits: Upfront or milestone deposits. These are often your best early-week cash source.
| OUTFLOWS (red section) | Payroll: Enter gross payroll. If bi-weekly, enter the full amount in the week it goes out. Subcontractor Payments: Note pay-when-paid clauses — subs typically get paid 30-45 days after GC pays you. Overhead: Fixed weekly amount. Tip: take monthly overhead ÷ 4.33 to get weekly figure. Owner Draw: Don't skip this — it's one of the most common causes of surprise cash shortages.
STEP 4 — READ THE SIGNALS
| 🔴 Red ending cash week | You are projected to fall below your safety threshold. Action needed NOW: Can you accelerate a draw request? Delay a material purchase? Push a sub payment one week? This is the whole point of the tool — catching this 4 weeks early.
| 🟠 Orange ending cash week | Warning zone — within 20% above your threshold. Not a crisis yet but watch it closely. Review what's scheduled that week and the week after.
| 🟢 Green ending cash week | Healthy — above 120% of your threshold. No immediate action needed.
STEP 5 — USE THE MASTER SUMMARY TAB
| 📊 Master Summary tab | Automatically consolidates all 5 job tabs. Shows inflows, outflows, net cash flow, and ending cash for each job side by side, week by week. Also shows company-wide combined ending cash with its own red zone threshold (set separately — typically higher than any single job threshold).
| Company Red Zone vs Job Red Zone | Each job tab has its own threshold (what's safe for that job). The Master Summary has a separate company-level threshold (what's safe for the whole business). You might be fine on individual jobs but still be dangerously low company-wide — or vice versa. Check both.
CONSTRUCTION-SPECIFIC TIPS
| Draw request lag | The most common mistake: entering a draw in the week you SUBMIT it, not the week you RECEIVE it. In construction, draws take 14–21 days from submission to bank deposit. Always enter draws in the week the cash is expected to actually land.
| Pay-when-paid (subs) | If your sub contracts include pay-when-paid clauses, your sub payment outflow shouldn't happen until AFTER you've received the corresponding draw. Model this correctly or your cash plan will show sub payments going out before inflows arrive — creating a false crisis on paper.
| Retainage timing | Retainage is rarely released on time. If the contract says 30 days after substantial completion, budget 60–90 days in your planner. Conservative retainage timing is always safer than optimistic.
COLOR & PROTECTION GUIDE
| 🟡 Yellow cells | Input cells — enter your data here. Always unlocked.
| 🔵 Blue cells | Formula cells — auto-calculated. Locked. Do not overwrite.
| 🔴 Red zone | Ending cash below your threshold — cash danger, action required.
| 🟠 Orange zone | Ending cash in warning range — monitor closely.
| 🟢 Green zone | Ending cash healthy — above 120% of threshold.
| Unprotect | Review → Unprotect Sheet → Password: CFO2026
Cash Flow Office ¦ cfo@cashflowoffice.com ¦ cashflowoffice.com ¦ © 2026 Darlene Martin ¦ Unprotect password: CFO2026